## Gantt Chart
Task Name | Duration | Start | Finish | Predecessors | Resource Names
SPRINT 1: Backend & System Setup | 5 days | 05/11/26 | 05/15/26
[US-20] Project setup: Express, MySQL, routes | 1 day | 05/11/26 | 05/11/26 |  | Min Thu
[US-1] Feed integrator: MAS scraping | 2 days | 05/12/26 | 05/13/26 | 2 | Min Thu
[US-2] Change detection & version comparison | 2 days | 05/13/26 | 05/14/26 | 3 | Min Thu
[RAG] RAG pipeline (Chroma + embeddings) | 2 days | 05/14/26 | 05/15/26 | 3 | Min Thu
[PII] PII filter service | 2 days | 05/14/26 | 05/15/26 | 8 | Min Thu
[LLM] LLM audit logging | 1 day | 05/15/26 | 05/15/26 | 5 | Min Thu
[US-3] Impact assessment (LLM) | 2 days | 05/12/26 | 05/13/26 | 2 | Eaint
[US-4] Alert generation & severity | 1 day | 05/14/26 | 05/14/26 | 8 | Eaint
[US-8] Dashboard summary API | 2 days | 05/14/26 | 05/15/26 | 9 | Eaint
[US-14] Regulatory sources API | 2 days | 05/11/26 | 05/12/26 |  | Hsu
[US-15] Regulations API (CRUD) | 3 days | 05/11/26 | 05/13/26 | 11 | Hsu
[US-19] Audit trail API | 1 day | 05/14/26 | 05/14/26 | 12 | Hsu
[US-18] Internal policies API | 2 days | 05/11/26 | 05/12/26 |  | Kay
[US-9] Tasks API (CRUD) | 3 days | 05/11/26 | 05/13/26 |  | Kay
[US-12] Compliance gaps API | 2 days | 05/13/26 | 05/14/26 | 12,14 | Kay
SPRINT 2: Frontend & Dashboard Views | 4 days | 05/18/26 | 05/21/26 | 1
[US-20] Sidebar + login + view switching | 2 days | 05/18/26 | 05/19/26 |  | Min Thu
[US-14/15] Sources + Regulations view | 3 days | 05/18/26 | 05/20/26 |  | Min Thu
[US-18/19] Policies + Audit trail view | 2 days | 05/20/26 | 05/21/26 | 18 | Min Thu
[US-5] Alerts view (badges, cards) | 2 days | 05/18/26 | 05/19/26 |  | Eaint
[US-6] Alert status update | 1 day | 05/20/26 | 05/20/26 | 21 | Eaint
[US-7] Alert filtering (client-side) | 1 day | 05/20/26 | 05/20/26 | 21 | Eaint
[US-8] Reports view (5 tabs, charts) | 2 days | 05/18/26 | 05/19/26 |  | Kay
[US-10] Tasks view - add form | 2 days | 05/18/26 | 05/19/26 |  | Kay
[US-11] Tasks - status + delete | 1 day | 05/20/26 | 05/20/26 | 25 | Kay
[US-13] Gaps view (CRUD, status) | 2 days | 05/18/26 | 05/19/26 |  | Hsu
[US-16] Changes view (impact badges) | 1 day | 05/20/26 | 05/20/26 | 27 | Hsu
[US-17] Impact dashboard (cards, sort) | 2 days | 05/18/26 | 05/19/26 |  | Hsu
SPRINT 3: Features, Testing & Polish | 4 days | 05/25/26 | 05/28/26 | 17
[US-23] CSV export | 1 day | 05/25/26 | 05/25/26 |  | Eaint
[US-24] Print compliance report | 1 day | 05/25/26 | 05/25/26 |  | Kay
[US-22] Dark mode + persistence | 1 day | 05/25/26 | 05/25/26 |  | Hsu
[US-25] Pagination (all tables) | 2 days | 05/25/26 | 05/26/26 |  | Hsu
Test: Alerts | 1 day | 05/26/26 | 05/26/26 | 31 | Eaint
Test: Tasks | 1 day | 05/26/26 | 05/26/26 | 32 | Kay
Test: Gaps, policies, regulations | 1 day | 05/26/26 | 05/26/26 | 34 | Hsu
Test: Feed integrator | 1 day | 05/26/26 | 05/26/26 | 33 | Min Thu
Test: Login/logout | 1 day | 05/26/26 | 05/26/26 | 33 | Eaint
Test: Edge cases | 1 day | 05/27/26 | 05/27/26 | 35,36 | Kay
Test: Reports & charts | 1 day | 05/27/26 | 05/27/26 | 36 | Kay
Bug fixes | 2 days | 05/27/26 | 05/28/26 | 38 | Min Thu
UI polish | 1 day | 05/27/26 | 05/27/26 | 38 | Min Thu
Full integration test | 1 day | 05/28/26 | 05/28/26 | 42 | Min Thu
Demo preparation | 1 day | 05/28/26 | 05/28/26 | 44 | All