## Gantt Data
Task Name | Duration | Start | Finish | Predecessors | Resource Names
Sprint 1: Backend & System Setup (24 SP, 47 hrs) | 5 days | 11/05/26 | 15/05/26
[US-20] Project setup: Express, MySQL, db.js, .env, routes | 1 day | 11/05/26 | 11/05/26 |  | Min Thu
[US-1] Feed integrator: MAS web scraping + deduplication | 2 days | 12/05/26 | 13/05/26 | 2 | Min Thu
[US-2] Regulation change detection & version comparison | 2 days | 13/05/26 | 14/05/26 | 3 | Min Thu
[US-3] Impact assessment engine (LLM-powered) | 2 days | 12/05/26 | 13/05/26 | 2 | Eaint
[US-4] Alert generation & severity mapping | 1 day | 14/05/26 | 14/05/26 | 5 | Eaint
[US-8] Dashboard summary API (summary, categories, trends) | 2 days | 14/05/26 | 15/05/26 | 6 | Eaint
[US-14] Regulatory sources API (GET/POST) | 2 days | 11/05/26 | 12/05/26 |  | Hsu
[US-15] Regulations knowledge base API (GET/POST/PUT) | 3 days | 11/05/26 | 13/05/26 | 8 | Hsu
[US-19] Audit trail API (GET with query filters) | 1 day | 14/05/26 | 14/05/26 | 9 | Hsu
[US-18] Internal policies API (GET/POST/PUT) | 2 days | 11/05/26 | 12/05/26 |  | Kay
[US-9] Tasks API (GET/POST/PATCH/DELETE) | 3 days | 11/05/26 | 13/05/26 |  | Kay
[US-12] Compliance gaps API (GET/POST/PATCH) | 2 days | 13/05/26 | 14/05/26 | 9,11 | Kay
[RAG] RAG pipeline (Chroma + OpenAI embeddings) | 2 days | 14/05/26 | 15/05/26 | 3 | Min Thu
[PII] PII filter service (NRIC, phone, email, credit card) | 2 days | 14/05/26 | 15/05/26 | 5 | Min Thu
[LLM] LLM audit logging (input, output, duration) | 1 day | 15/05/26 | 15/05/26 | 14 | Min Thu