## Gantt Data
Task Name | Duration | Start | Finish | Predecessors | Resource Names
Sprint 2: Frontend & Dashboard Views (28 SP, 41 hrs) | 4 days | 18/05/26 | 21/05/26
[US-20] Sidebar navigation + login overlay + view switching | 2 days | 18/05/26 | 19/05/26 |  | Min Thu
[US-14/15] Sources + Regulations view (search, pagination) | 3 days | 18/05/26 | 20/05/26 |  | Min Thu
[US-18/19] Policies view + Audit trail view (filters) | 2 days | 20/05/26 | 21/05/26 | 2 | Min Thu
[US-5] Alerts view (severity badges, summary cards) | 2 days | 18/05/26 | 19/05/26 |  | Eaint
[US-6] Alert status update (dropdown, PATCH) | 1 day | 20/05/26 | 20/05/26 | 5 | Eaint
[US-7] Alert filtering (severity + status, client-side) | 1 day | 20/05/26 | 20/05/26 | 5 | Eaint
[US-8] Reports view (5 tabs, Chart.js charts) | 2 days | 18/05/26 | 19/05/26 |  | Kay
[US-10] Tasks view - add task form | 2 days | 18/05/26 | 19/05/26 |  | Kay
[US-11] Tasks - status dropdown + delete button | 1 day | 20/05/26 | 20/05/26 | 9 | Kay
[US-13] Gaps view (CRUD form, status dropdown) | 2 days | 18/05/26 | 19/05/26 |  | Hsu
[US-16] Changes view (version history, impact badges) | 1 day | 20/05/26 | 20/05/26 | 11 | Hsu
[US-17] Impact assessment dashboard (cards, sorting) | 2 days | 18/05/26 | 19/05/26 |  | Hsu