## Gantt Data
Task Name | Duration | Start | Finish | Predecessors | Resource Names
Sprint 3: Features, Testing & Polish (11 SP, 56 hrs) | 4 days | 25/05/26 | 28/05/26
[US-23] CSV export (alerts) | 1 day | 25/05/26 | 25/05/26 |  | Eaint
[US-24] Print formatted compliance report | 1 day | 25/05/26 | 25/05/26 |  | Kay
[US-22] Dark mode toggle + localStorage persistence | 1 day | 25/05/26 | 25/05/26 |  | Hsu
[US-25] Pagination controls (all tables, 10 per page) | 2 days | 25/05/26 | 26/05/26 |  | Hsu
Test: Alerts (view, filter, update status) | 1 day | 26/05/26 | 26/05/26 | 2 | Eaint
Test: Tasks (create, update, delete, deadlines) | 1 day | 26/05/26 | 26/05/26 | 3 | Kay
Test: Gaps, policies, regulations, sources | 1 day | 26/05/26 | 26/05/26 | 5 | Hsu
Test: Feed integrator (scrape, alerts, changes, impact) | 1 day | 26/05/26 | 26/05/26 | 4 | Min Thu
Test: Login/logout with all roles | 1 day | 26/05/26 | 26/05/26 | 4 | Eaint
Test: Edge cases & error handling | 1 day | 27/05/26 | 27/05/26 | 6,7 | Kay
Test: Reports (charts, tabs, print) | 1 day | 27/05/26 | 27/05/26 | 7 | Kay
Bug fixes from testing | 2 days | 27/05/26 | 28/05/26 | 9 | Min Thu
UI polish (toasts, spinners, welcome banner) | 1 day | 27/05/26 | 27/05/26 | 9 | Min Thu
Full integration test (end-to-end pipeline) | 1 day | 28/05/26 | 28/05/26 | 13 | Min Thu
Prepare demo script and walkthrough | 1 day | 28/05/26 | 28/05/26 | 15 | All